## Executive Roadmap
🚀 SMART HOME E-COMMERCE - 12 MONTH MASTER WORK PLAN
Digital Products + Dropshipping + Hybrid Bundles ¦ Target: SAR 500,000/month by Month 12
FOUR-PHASE EXECUTION ROADMAP
Phase | Timeline | Focus | Key Deliverables | Revenue Target | Investment | Success Metrics
Phase 1: Foundation | Weeks 1-4 | Setup & First Digital Product | Salla store live, First guide published, Social accounts active | SAR 500 | SAR 500 | Store live, 1 product, 100 followers
Phase 2: Digital Launch | Weeks 5-12 | Build Digital Product Library | 3 guides + 1 bundle live, Email list 500+, Content engine running | SAR 5,000 | SAR 1,500 | 50 digital sales, 500 email subs
Phase 3: Add Dropshipping | Weeks 13-20 | Launch Physical Products | 15 products live, First hybrid bundles, KSA Drop integrated | SAR 15,000 | SAR 2,000 | 100 orders, 5 hybrid bundles
Phase 4: Scale | Weeks 21-52 | Grow & Optimize | Full product catalog, Ads running, Systems automated | SAR 50,000+/mo | SAR 5,000+ | Break-even, repeat customers
KEY MILESTONES & DEADLINES
Milestone | Deadline | Owner | Dependencies | Status
Salla Store Live | Week 1 | Fahad | Domain, CR | ⬜ Not Started
First Digital Product Published | Week 3 | Fahad | Store live, Content ready | ⬜ Not Started
Social Media Accounts Active | Week 2 | Fahad | Branding complete | ⬜ Not Started
Email List Reaches 100 | Week 6 | Fahad | Lead magnet live | ⬜ Not Started
Second Digital Product Live | Week 6 | Fahad | First product validated | ⬜ Not Started
Third Digital Product + Bundle | Week 10 | Fahad | Content pipeline | ⬜ Not Started
KSA Drop Account Active | Week 12 | Fahad | Test products identified | ⬜ Not Started
First 10 Physical Products Live | Week 14 | Fahad | KSA Drop ready | ⬜ Not Started
First Hybrid Bundle Live | Week 16 | Fahad | Digital + Physical ready | ⬜ Not Started
Email List Reaches 500 | Week 12 | Fahad | Content marketing active | ⬜ Not Started
First SAR 10,000 Month | Week 20 | Fahad | All systems running | ⬜ Not Started
Break-Even Achieved | Week 26 | Fahad | Revenue > Costs | ⬜ Not Started
SAR 50,000/Month | Week 40 | Fahad | Scaling systems | ⬜ Not Started

## Phase 1 - Foundation
PHASE 1: FOUNDATION (WEEKS 1-4)
Goal: Store live, first digital product published, social presence established
WEEK 1: BUSINESS SETUP
Day | Task | Details | Time Est. | Tools/Resources | Deliverable | Done
Day 1 | Register Salla Account | Go to salla.com, sign up with your email, verify phone | 1 hour | salla.com | Active Salla account | ☐
Day 1 | Choose Store Name (Arabic + English) | بيت ذكي / Smart Home KSA or similar, check domain availability | 1 hour | Namecheap, Salla | Final store name decided | ☐
Day 1 | Select Salla Plan | Start with FREE plan (upgrade to Plus SAR 99 when adding digital products) | 30 min | Salla dashboard | Plan selected | ☐
Day 2 | Connect Domain | Point your domain to Salla OR use free Salla subdomain to start | 1 hour | Domain registrar | Domain connected | ☐
Day 2 | Store Basic Settings | Logo, colors (use brand guidelines), contact info, about page | 2 hours | Canva for logo | Store branding complete | ☐
Day 3 | Setup Payment Methods | Enable Mada, Apple Pay, STC Pay, Tabby, Tamara | 1 hour | Salla > Settings > Payments | All payment methods active | ☐
Day 3 | Setup Shipping | Enable standard shipping SAR 25-35, free shipping over SAR 200 | 1 hour | Salla > Settings > Shipping | Shipping configured | ☐
Day 4 | Create Store Pages | About Us, Contact, FAQ, Privacy Policy, Return Policy | 3 hours | Templates in Salla | 5 pages published | ☐
Day 5 | Legal: Review Maroof | Register on maroof.sa for e-commerce trust badge | 1 hour | maroof.sa | Maroof registration started | ☐
Day 6 | Install Essential Apps | Google Analytics, Facebook Pixel, WhatsApp chat widget | 2 hours | Salla App Store | Analytics tracking live | ☐
Day 7 | Store Review & Test | Test checkout flow, mobile view, payment processing | 2 hours | Your phone + laptop | Store ready for products | ☐
WEEK 2: BRANDING & SOCIAL MEDIA
Day | Task | Details | Time Est. | Tools/Resources | Deliverable | Done
Day 8 | Create Brand Kit | Logo variations, color palette, fonts, brand voice guidelines | 3 hours | Canva Pro | Brand kit document | ☐
Day 8 | Design Social Media Templates | 5 Instagram post templates, 5 story templates, Twitter header | 2 hours | Canva | 15 templates ready | ☐
Day 9 | Create Twitter/X Account | @SmartHomeKSA or similar, complete bio, link to store | 1 hour | twitter.com | Twitter account live | ☐
Day 9 | Create Instagram Account | Same handle, business account, link to store | 1 hour | instagram.com | Instagram account live | ☐
Day 10 | Create YouTube Channel | For future video tutorials, branded channel art | 2 hours | youtube.com | YouTube channel ready | ☐
Day 10 | Create TikTok Account | Same branding, business account | 1 hour | tiktok.com | TikTok account live | ☐
Day 11 | Write First 10 Social Posts | Mix of tips, questions, teaser content for upcoming guide | 3 hours | Your knowledge | 10 posts scheduled | ☐
Day 12 | Create Lead Magnet | Free 5-page PDF "5 أخطاء في المنزل الذكي" (5 Smart Home Mistakes) | 4 hours | Google Docs, Canva | Lead magnet PDF ready | ☐
Day 13 | Setup Email Collection | Salla email capture OR Mailchimp free plan integration | 2 hours | Salla/Mailchimp | Email signup working | ☐
Day 14 | Post First Week Content | Introduction post, 3 tips, 1 question to followers | 2 hours | Social platforms | 5 posts live | ☐
WEEK 3: FIRST DIGITAL PRODUCT CREATION
Day | Task | Details | Time Est. | Tools/Resources | Deliverable | Done
Day 15 | Outline HA Beginner Guide | Complete chapter structure, 40-60 pages target | 3 hours | Google Docs | Full outline complete | ☐
Day 15 | Gather Screenshots/Images | HA interface, installation steps, device examples | 2 hours | Your HA setup | Image folder ready | ☐
Day 16 | Write Chapter 1: What is HA | Introduction, benefits, comparison to other systems | 4 hours | Google Docs | Chapter 1 draft (8 pages) | ☐
Day 17 | Write Chapter 2: Installation | All installation methods with step-by-step | 5 hours | Google Docs | Chapter 2 draft (12 pages) | ☐
Day 18 | Write Chapter 3: First Setup | Initial configuration, adding first device | 4 hours | Google Docs | Chapter 3 draft (10 pages) | ☐
Day 19 | Write Chapter 4: Automations | Creating first automations, examples | 4 hours | Google Docs | Chapter 4 draft (10 pages) | ☐
Day 20 | Write Chapter 5: Mobile & Backup | App setup, backup strategies, security | 3 hours | Google Docs | Chapter 5 draft (8 pages) | ☐
Day 21 | Edit & Review Full Guide | Proofread, check screenshots, ensure flow | 4 hours | Google Docs | Edited manuscript | ☐
WEEK 4: PRODUCT LAUNCH
Day | Task | Details | Time Est. | Tools/Resources | Deliverable | Done
Day 22 | Design Guide Cover | Professional PDF cover, back cover, table of contents | 3 hours | Canva | Cover design ready | ☐
Day 22 | Format PDF | Consistent styling, headers, page numbers, clickable TOC | 3 hours | Google Docs > PDF | Formatted PDF | ☐
Day 23 | Upgrade to Salla Plus | SAR 99/month to enable digital product sales | 30 min | Salla | Plus plan active | ☐
Day 23 | Create Product Listing | Title, description, price SAR 49, images, auto-delivery setup | 2 hours | Salla dashboard | Product page live | ☐
Day 24 | Test Purchase Flow | Buy your own product, check delivery works | 1 hour | Your card | Delivery confirmed | ☐
Day 24 | Create Sales Page | Long-form description, benefits, who its for, FAQ | 3 hours | Salla page builder | Sales page ready | ☐
Day 25 | Create Launch Content | 5 social posts, 1 email, announcement graphics | 4 hours | Canva | Launch assets ready | ☐
Day 26 | SOFT LAUNCH | Share with friends/family first, collect feedback | 2 hours | WhatsApp groups | First 5 sales target | ☐
Day 27 | PUBLIC LAUNCH | Post on all social channels, send email to list | 3 hours | All platforms | Launched! | ☐
Day 28 | Monitor & Respond | Answer questions, track sales, gather feedback | 2 hours | Salla + Social | Week 1 metrics logged | ☐

## Phase 2 - Digital Library
PHASE 2: BUILD DIGITAL PRODUCT LIBRARY (WEEKS 5-12)
Goal: 3 guides + 1 bundle live, 500 email subscribers, content marketing engine running
WEEKLY SCHEDULE - PHASE 2
Week | Primary Focus | Content to Create | Marketing Actions | Target Metrics | Revenue Target
Week 5 | Analyze + Plan Second Product | Review feedback on Guide 1, outline Zigbee Guide | Daily social posts, engage community | 10 sales, 150 email subs | SAR 500
Week 6 | Create Zigbee Guide (Part 1) | Write chapters 1-3 of Zigbee Guide | 3 blog posts, 2 tutorial threads | 15 sales, 200 email subs | SAR 750
Week 7 | Create Zigbee Guide (Part 2) | Write chapters 4-6, edit, format | YouTube short tutorials start | 20 sales, 250 email subs | SAR 1,000
Week 8 | Launch Zigbee Guide (SAR 59) | Publish, create sales page, launch campaign | Email launch, social blitz | 25 sales, 300 email subs | SAR 1,250
Week 9 | Create Dashboard Templates | Design 5 HA dashboard templates package | Case study from customer | 30 sales, 350 email subs | SAR 1,500
Week 10 | Create First Bundle | Bundle: HA Guide + Zigbee Guide = SAR 89 | Bundle promotion campaign | 35 sales, 400 email subs | SAR 1,750
Week 11 | Content Marketing Push | Guest post outreach, influencer contacts | Paid promotion test (SAR 200) | 40 sales, 450 email subs | SAR 2,000
Week 12 | Prepare for Dropshipping | Research KSA Drop, select test products | Email sequence automation | 50 sales, 500 email subs | SAR 2,500
CONTENT CREATION CALENDAR
Content Type | Frequency | Day(s) | Topics | Platform | Purpose
Twitter Thread | 2x/week | Mon, Thu | How-to tips, HA features, Smart home myths | Twitter/X | Build authority
Instagram Post | 3x/week | Mon, Wed, Fri | Visual tips, setup photos, before/after | Instagram | Visual audience
Instagram Story | Daily | Every day | Quick tips, polls, behind-the-scenes | Instagram | Engagement
Blog Post | 1x/week | Tuesday | Long-form tutorials, SEO content | Website/Salla | SEO traffic
YouTube Short | 2x/week | Wed, Sat | 60-sec tips, product demos | YouTube | Discovery
Email Newsletter | 1x/week | Sunday | Weekly roundup, exclusive tips, offers | Mailchimp | Nurture leads
TikTok | 3x/week | Tue, Thu, Sat | Quick tips, trending formats | TikTok | Viral potential

## Phase 3 - Dropshipping
PHASE 3: ADD DROPSHIPPING (WEEKS 13-20)
WEEKLY EXECUTION PLAN
Week | Primary Focus | Tasks | Products to Add | Target Orders | Revenue Target
Week 13 | KSA Drop Setup | Create account, study catalog, understand process, test order | 0 (research only) | 0 | SAR 2,500 (digital)
Week 14 | First 5 Products Live | Add 5 smart plugs/sensors, write descriptions, set prices | 5 products | 5 orders | SAR 3,000
Week 15 | Expand to 10 Products | Add LED strips, bulbs, hubs based on guide mentions | 5 more products | 10 orders | SAR 4,000
Week 16 | First Hybrid Bundle | Create "Starter Kit": HA Guide + Motion Sensor = SAR 79 | 1 hybrid bundle | 15 orders | SAR 5,000
Week 17 | Expand to 15 Products | Add coordinators, switches, specialized sensors | 5 more products | 20 orders | SAR 6,000
Week 18 | Second Hybrid Bundle | Create "Zigbee Master": Zigbee Guide + Coordinator = SAR 109 | 1 more bundle | 25 orders | SAR 8,000
Week 19 | M5azn Evaluation | Test M5azn for automation, compare to KSA Drop | 0 (evaluation) | 30 orders | SAR 10,000
Week 20 | Full Product Launch | 20 products + 3 bundles live, all systems working | 5 more products | 40 orders | SAR 15,000
PRODUCT SELECTION CHECKLIST (What to Add First)
Priority | Product Category | Example Products | Price Range | Margin | Pairs With Guide
1 | Smart Plugs | WiFi plug, Zigbee plug, energy monitor plug | SAR 49-89 | 25-35% | HA Guide, Energy Guide
2 | Motion Sensors | Zigbee motion, PIR sensor | SAR 35-59 | 30-40% | HA Guide, Zigbee Guide
3 | Door/Window Sensors | Zigbee contact sensor | SAR 29-49 | 30-40% | HA Guide, Zigbee Guide
4 | Zigbee Coordinators | Sonoff Zigbee 3.0, Conbee II | SAR 59-99 | 25-35% | Zigbee Guide (ESSENTIAL)
5 | Smart LED Strips | 2m, 5m RGB strips | SAR 69-129 | 30-40% | Lighting Guide
6 | Smart Bulbs | Zigbee bulbs, WiFi bulbs | SAR 39-69 | 25-35% | Lighting Guide
7 | Temperature Sensors | Temp/humidity Zigbee | SAR 35-55 | 30-40% | HA Guide, Energy Guide
8 | Water Leak Sensors | Zigbee water detector | SAR 45-65 | 30-40% | HA Guide
9 | IR Remote Controllers | Broadlink, Tuya IR | SAR 49-79 | 25-35% | HA Guide
10 | Smart Curtain Motors | Zigbee curtain motor | SAR 129-199 | 20-30% | Premium bundle
KSA DROP ORDER PROCESS (Step-by-Step)
1. Customer orders on your Salla store
2. You receive order notification (email + Salla app)
3. Open KSA Drop WhatsApp and send order details:
- Customer name, phone, address
- Product name + SKU
- Payment method (prepaid/COD)
4. KSA Drop confirms availability + shipping cost
5. KSA Drop ships within 24-48 hours
6. Customer receives in 3-5 days
7. KSA Drop pays you weekly (every Sunday)
⚠️ IMPORTANT: Always confirm stock before promising delivery dates!

## Phase 4 - Scale
PHASE 4: SCALE TO SAR 50,000+/MONTH (WEEKS 21-52)
MONTHLY TARGETS & ACTIONS
Month | Focus | Key Actions | Products | Orders | Revenue Target | Profit Target
Month 6 | Optimize & Automate | Setup M5azn automation, email sequences, retargeting ads | 25 products | 80/mo | SAR 20,000 | SAR 7,000
Month 7 | Paid Ads Launch | Start Instagram + TikTok ads SAR 2,000 budget | 30 products | 120/mo | SAR 30,000 | SAR 9,000
Month 8 | Content Scaling | Hire VA for social media, create video course | 35 products | 150/mo | SAR 35,000 | SAR 11,000
Month 9 | Premium Products | Add higher-margin items (curtain motors, hubs) | 40 products | 180/mo | SAR 40,000 | SAR 13,000
Month 10 | Video Course Launch | Launch SAR 299 video course on HA | 40 products | 200/mo | SAR 45,000 | SAR 16,000
Month 11 | Ramadan Prep | Stock up, create Ramadan bundles, increase ad spend | 45 products | 250/mo | SAR 50,000 | SAR 18,000
Month 12 | Review & Plan Year 2 | Analyze what worked, plan expansion | 50 products | 300/mo | SAR 60,000 | SAR 22,000
SYSTEMS TO AUTOMATE
System | Tool/Service | Cost | Time Saved | When to Implement
Order fulfillment | M5azn Salla Integration | SAR 49-199/mo | 5+ hrs/week | Month 6 (50+ orders)
Email marketing | Mailchimp/Salla Email | Free-SAR 50/mo | 3+ hrs/week | Month 3
Abandoned cart | Salla built-in | Included | 2+ hrs/week | Week 1
Social scheduling | Buffer/Later | SAR 50/mo | 4+ hrs/week | Month 4
Customer support | WhatsApp Business + Templates | Free | 3+ hrs/week | Week 2
Accounting | Salla Reports + Sheet | Free | 2+ hrs/week | Month 1
Inventory alerts | M5azn alerts | Included | 1+ hr/week | Month 6

## Financial Tracker
FINANCIAL TRACKER - BUDGET & REVENUE
STARTUP COSTS (ONE-TIME)
Item | Cost (SAR) | When | Notes
Domain name (1 year) | 50 | Week 1 | Optional if using Salla subdomain
Logo design (Canva Pro) | 0 | Week 1 | DIY with Canva free
First test purchase | 50 | Week 4 | Test your own checkout
Lead magnet design | 0 | Week 2 | DIY
TOTAL STARTUP | 100 |  | Minimal investment needed
MONTHLY OPERATING COSTS
Item | Month 1-3 | Month 4-6 | Month 7-12 | Notes
Salla Plus subscription | 99 | 99 | 99 | Required for digital products
M5azn subscription | 0 | 49 | 99 | Add when scaling dropshipping
Email marketing | 0 | 0 | 50 | Free tier then upgrade
Social media tools | 0 | 50 | 50 | Buffer or Later
Marketing/Ads budget | 0 | 500 | 2000 | Start small, scale with profit
Miscellaneous | 100 | 200 | 300 | Buffer for unexpected costs
TOTAL MONTHLY | 199 | 898 | 2598
REVENUE & PROFIT PROJECTIONS
Month | Digital Rev | Physical Rev | Bundle Rev | Total Revenue | Costs | NET PROFIT
Month 1 | 500 | 0 | 0 | 500 | 199 | 301
Month 2 | 1500 | 0 | 0 | 1500 | 199 | 1301
Month 3 | 2500 | 0 | 0 | 2500 | 199 | 2301
Month 4 | 3000 | 1500 | 500 | 5000 | 898 | 4102
Month 5 | 3500 | 3000 | 1500 | 8000 | 898 | 7102
Month 6 | 4000 | 6000 | 5000 | 15000 | 898 | 14102
Month 7 | 5000 | 10000 | 10000 | 25000 | 2598 | 22402
Month 8 | 6000 | 12000 | 12000 | 30000 | 2598 | 27402
Month 9 | 7000 | 15000 | 13000 | 35000 | 2598 | 32402
Month 10 | 8000 | 17000 | 15000 | 40000 | 2598 | 37402
Month 11 | 10000 | 20000 | 20000 | 50000 | 2598 | 47402
Month 12 | 12000 | 23000 | 25000 | 60000 | 2598 | 57402

## KPIs & Metrics
KEY PERFORMANCE INDICATORS (KPIs) TO TRACK
WEEKLY TRACKING METRICS
KPI | Target Week 4 | Target Week 12 | Target Week 24 | Target Week 52 | How to Track
Total Revenue (SAR) | 500 | 5,000 | 25,000 | 60,000 | Salla Dashboard
Digital Product Sales | 10 | 50 | 150 | 400 | Salla Reports
Physical Orders | 0 | 40 | 200 | 800 | Salla + KSA Drop
Hybrid Bundle Sales | 0 | 20 | 100 | 300 | Salla Reports
Website Visitors | 500 | 3,000 | 15,000 | 50,000 | Google Analytics
Conversion Rate | 2% | 2.5% | 3% | 3.5% | GA + Salla
Email Subscribers | 100 | 500 | 2,000 | 5,000 | Mailchimp
Email Open Rate | 30% | 35% | 35% | 35% | Mailchimp
Social Followers (Total) | 200 | 1,000 | 5,000 | 15,000 | Native analytics
Average Order Value (SAR) | 50 | 100 | 150 | 200 | Salla Reports
Customer Return Rate | 5% | 10% | 15% | 20% | Salla Reports
COD Success Rate | N/A | 75% | 80% | 85% | Manual tracking
Net Profit Margin | 90% | 60% | 50% | 45% | Your spreadsheet
WEEKLY REVIEW CHECKLIST (Every Sunday)
Task | Time | Purpose
Review Salla dashboard sales | 10 min | Know your numbers
Check email list growth | 5 min | Track lead generation
Review social analytics | 15 min | Understand what content works
Check KSA Drop payouts | 5 min | Confirm payments received
Review customer messages/questions | 15 min | Identify content ideas
Update tracking spreadsheet | 10 min | Historical data
Plan next week content | 30 min | Stay consistent
Identify 1 thing to improve | 10 min | Continuous improvement

## Content Bank
CONTENT IDEAS BANK - 100+ IDEAS TO POST
EDUCATIONAL CONTENT (Build Authority)
# | Content Idea (Arabic Topic) | Format | Platform | Links to Product
1 | ما هو Home Assistant؟ شرح مبسط | Thread | Twitter | HA Guide
2 | ٥ أسباب للتحول للمنزل الذكي | Carousel | Instagram | All guides
3 | الفرق بين WiFi و Zigbee و Matter | Video | YouTube/TikTok | Zigbee Guide
4 | كيف توفر فاتورة الكهرباء بالتقنية | Thread | Twitter | Energy Guide
5 | أفضل ٥ أجهزة للمبتدئين | Reel | Instagram | Products
6 | شرح الأتمتة في ٦٠ ثانية | Short | TikTok | HA Guide
7 | لماذا أستخدم Home Assistant بدل Alexa؟ | Blog | Website | HA Guide
8 | كيف تبدأ بدون أي خبرة تقنية | Thread | Twitter | Beginner Bundle
9 | أخطاء شائعة في المنزل الذكي | Carousel | Instagram | All guides
10 | جولة في منزلي الذكي | Video | YouTube | All products
PROMOTIONAL CONTENT (Drive Sales)
# | Content Idea | Format | Platform | Offer
1 | إطلاق دليل Home Assistant الجديد! | Announcement | All | Launch price
2 | عرض نهاية الأسبوع - ٢٠٪ خصم | Story + Post | Instagram | 20% off
3 | اشتري الدليل واحصل على حساس مجاني | Carousel | Instagram | Bundle deal
4 | آخر ٥ نسخ بالسعر القديم | Story | Instagram | Urgency
5 | حزمة المبتدئ الكاملة متوفرة | Video | TikTok | Bundle
6 | رأي عميل: قبل وبعد | Testimonial | All | Social proof
7 | سؤال وجواب مباشر الليلة | Live | Instagram | Engagement
8 | هدية للمشتركين الجدد | Email | Mailchimp | Lead magnet
ENGAGEMENT CONTENT (Build Community)
# | Content Idea | Format | Platform | Goal
1 | استفتاء: أي جهاز تريد شرحه؟ | Poll | Twitter/Instagram | Engagement
2 | شاركنا صورة منزلك الذكي | UGC Request | Instagram | Community
3 | سؤال: ما أول أتمتة عملتها؟ | Question | Twitter | Discussion
4 | تحدي: أتمتة في ٥ دقائق | Challenge | TikTok | Viral potential
5 | جلسة AMA - اسألني أي شيء | Live Q&A | Instagram | Trust building
6 | من يستخدم Home Assistant هنا؟ 🙋 | Question | Twitter | Find audience
7 | شاركنا أكبر تحدي واجهته | Story | Instagram | Content ideas
8 | هل تفضل الدليل العربي أم الإنجليزي؟ | Poll | Twitter | Validation

## Daily Schedule
IDEAL DAILY & WEEKLY SCHEDULE
DAILY TIME BLOCKS (2-3 hours/day)
Time Block | Duration | Activity | Tools | Days
Morning (7-8 AM) | 30 min | Check orders & messages | Salla App, WhatsApp | Daily
Morning (8-9 AM) | 30 min | Social media engagement | Twitter, Instagram | Daily
Midday (12-1 PM) | 30 min | Content creation OR | Canva, Docs | Mon-Fri
Afternoon (4-5 PM) | 30 min | Post scheduled content | Buffer/Native | Daily
Evening (9-10 PM) | 60 min | Deep work: Writing/Product | Quiet time | Mon-Thu
Weekend | 3-4 hours | Batch content creation | All tools | Sat only
WEEKLY TASK DISTRIBUTION
Day | Focus Area | Main Tasks | Time
Saturday | Content Batch Day | Create all social content for the week, write blog post | 4 hours
Sunday | Review & Plan | Weekly metrics review, plan next week, respond to customers | 2 hours
Monday | Marketing | Email newsletter, engage with community, outreach | 2 hours
Tuesday | Product Work | Write guide content, improve products, test flows | 2 hours
Wednesday | Content Creation | Record videos, create graphics, write threads | 2 hours
Thursday | Business Development | Research new products, competitor analysis, partnerships | 2 hours
Friday | Light Day | Minimal work - check orders, respond to urgent messages only | 30 min
TOTAL TIME COMMITMENT BY PHASE
Phase | Hours/Week | Main Activities
Phase 1 (Weeks 1-4) | 15-20 hours | Setup, first product creation, learning
Phase 2 (Weeks 5-12) | 10-15 hours | Content creation, marketing, community
Phase 3 (Weeks 13-20) | 12-18 hours | Adding products, fulfillment, optimization
Phase 4 (Weeks 21+) | 8-12 hours | Maintenance, scaling, automation

## Tools & Resources
COMPLETE TOOLS & RESOURCES LIST
ESSENTIAL TOOLS (Must Have)
Tool | Purpose | Cost | URL | Priority
Salla | E-commerce platform | SAR 99/mo (Plus) | salla.com | ★★★★★
KSA Drop | Dropshipping supplier | Free | ksadrop.com | ★★★★★
Canva | Design graphics | Free / SAR 50/mo | canva.com | ★★★★★
Google Docs | Write content | Free | docs.google.com | ★★★★★
WhatsApp Business | Customer support | Free | whatsapp.com | ★★★★★
Google Analytics | Track website | Free | analytics.google.com | ★★★★★
OPTIONAL TOOLS (Nice to Have)
Tool | Purpose | Cost | URL | When to Add
M5azn | Automated dropshipping | SAR 49-199/mo | m5azn.com | Month 4-6
Mailchimp | Email marketing | Free up to 500 | mailchimp.com | Month 2
Buffer | Social scheduling | SAR 50/mo | buffer.com | Month 4
Notion | Project management | Free | notion.so | Anytime
ChatGPT Plus | Content assistance | SAR 75/mo | openai.com | Optional
Descript | Video editing | Free tier | descript.com | Month 6
LEARNING RESOURCES
Resource | Topic | Type | URL
Salla Academy | E-commerce basics | Free courses | academy.salla.com
YouTube: Smart Home Junkie | Home Assistant tutorials | Videos | youtube.com
Home Assistant Docs | Technical reference | Documentation | home-assistant.io
Zigbee2MQTT | Zigbee device info | Documentation | zigbee2mqtt.io
Arabic Tech Twitter | Market trends | Community | twitter.com (search)
Salla Community | Seller tips | Forum | community.salla.com